## Sheet1
Task ID | User Story | Priority | Estimated Hours | Sprint
US01 | As a student, I want to log in using my university ID so that I can access my profile. | High | 12 | Sprint 1
US02 | As a teacher, I want to view a real-time list of present students so that I can track attendance. | High | 16 | Sprint 1
US03 | As a system, I want to detect if a student is within 10 meters of the classroom so that attendance can be marked automatically. | High | 24 | Sprint 1
US04 | As a student, I want to get a notification when my attendance is marked so that I know it was recorded. | Medium | 8 | Sprint 1
US05 | As an admin, I want to manually override attendance in case of technical issues so that attendance records remain correct. | Low | 10 | Sprint 1
US06 | As a system, I want to prompt the user for biometric (Face ID) authentication before finalizing attendance. | High | 20 | Sprint 2
US07 | As a teacher, I want the dashboard to show whether a student was verified via Location or Face ID. | Medium | 12 | Sprint 2